## QA Test Plan
ID | Category | Sub-Category | Test Case | Steps | Expected Result | Priority | Status | Notes | XCUITest Name
TC-001 | Mood Logging | Day View | Log mood from Day View list | 1. Open app 2. Tap a mood button on today's row | Mood saved, entry appears with correct color and icon | P1 | PASS |  | MoodLoggingEmptyStateTests/testLogMood_Great_FromEmptyState MoodLoggingWithDataTests/testLogMood_Average_WhenDataExists
TC-002 | Mood Logging | Day View | Log mood from header quick-entry | 1. Open Day View 2. Tap Add Mood in header 3. Select a mood | Mood saved with entryType .header, header updates to show logged mood | P1 | PASS |  | HeaderMoodLoggingTests/testLogMood_FromHeader_CreatesEntry
TC-003 | Mood Logging | Day View | Replace existing mood for today | 1. Log mood as Good 2. Log mood as Great for same day | Previous entry deleted, new entry created, no duplicates | P1 | PASS |  | MoodReplacementTests/testReplaceMood_NoDuplicates
TC-004 | Mood Logging | Day View | Verify all side effects fire | 1. Log a mood 2. Check HealthKit (if enabled) 3. Check widget 4. Check watch 5. Check analytics | HealthKit synced, widget reloaded, watch notified, streak updated, analytics event sent | P1 | N/A - XCUITest | Cannot verify HealthKit/widget/watch side effects from XCUITest
TC-005 | Mood Logging | Widget | Log mood via interactive widget | 1. Add FeelsVoteWidget to home screen 2. Tap a mood button | Mood logged with entryType .widget, widget updates to show stats | P1 | RED | Widget interaction not testable in XCUI
TC-006 | Mood Logging | Widget | Widget voting with expired trial | 1. Let trial expire 2. Tap mood on widget | App opens to paywall instead of logging | P2 | RED | Widget interaction not testable in XCUI
TC-007 | Mood Logging | Watch | Log mood from Apple Watch | 1. Open Feels on watch 2. Tap a mood button | Mood logged with entryType .watch, syncs to phone via WCSession | P1 | RED | watchOS not testable in iOS simulator
TC-008 | Mood Logging | Watch | Watch shows already-rated state | 1. Log mood on phone 2. Open watch app | Watch shows today's mood instead of voting buttons | P2 | RED | watchOS not testable in iOS simulator
TC-009 | Mood Logging | Siri | Log mood via Siri | 1. Say "Log my mood as great in Feels" | Siri confirms mood logged, entry created with entryType .siri | P2 | RED | Siri not testable in XCUI
TC-010 | Mood Logging | Siri | Check today's mood via Siri | 1. Log a mood 2. Say "What's my mood today in Feels" | Siri reads back today's mood | P2 | RED | Siri not testable in XCUI
TC-011 | Mood Logging | Siri | Get streak via Siri | 1. Say "Check my streak in Feels" | Siri reads back current streak count | P3 | RED | Siri not testable in XCUI
TC-012 | Mood Logging | Shortcuts | Log mood via Shortcuts app | 1. Create Shortcut with LogMoodIntent 2. Run shortcut 3. Select mood | Mood logged with entryType .shortcut | P2 | RED | Shortcuts app not testable in XCUI
TC-013 | Mood Logging | Notification | Log mood from notification action | 1. Receive daily reminder notification 2. Long-press or expand 3. Tap a mood action button | Mood logged with entryType .notification | P1 | RED | Notification action requires system UI
TC-014 | Mood Logging | Control Center | Log mood from Control Center | 1. Add Feels to Control Center 2. Tap mood button | Mood logged with entryType .controlCenter | P2 | RED | Control Center requires system UI
TC-015 | Mood Logging | Live Activity | Log mood from Live Activity | 1. Have active Live Activity 2. Tap mood button on Lock Screen | Mood logged with entryType .liveActivity, activity updates | P2 | RED | Live Activity interaction not testable in XCUI
TC-016 | Mood Logging | Edge Case | Timezone change across midnight | 1. Set timezone to EST, log mood at 11:59 PM 2. Change timezone to PST (now 8:59 PM) | Entry stays on correct calendar date, no duplicate for new timezone date | P2 | RED | Requires system clock manipulation
TC-017 | Mood Logging | Edge Case | DST transition | 1. Log mood during spring-forward or fall-back hour | Entry assigned to correct date despite clock change | P3 | RED | Requires system clock manipulation (DST)
TC-018 | Mood Logging | Edge Case | Leap year Feb 29 | 1. Set device date to Feb 29 of a leap year 2. Log mood | Entry saved for Feb 29, appears correctly in Month/Year views | P3 | RED | Requires leap year system date
TC-019 | Day View | Display | Entries grouped by year/month | 1. Have entries across multiple months 2. Open Day View | Entries grouped under correct month/year headers, sorted newest first | P1 | PASS |  | DayViewGroupingTests/testEntries_GroupedBySectionHeaders
TC-020 | Day View | Display | Empty state with no entries | 1. Clear all data 2. Open Day View | Empty state message shown, no crashes | P2 | PASS |  | EmptyStateTests/testEmptyState_ShowsNoDataMessage
TC-021 | Day View | Styles | Switch between all 20 day view styles | 1. Go to Customize 2. Select each style: classic, minimal, compact, bubble, grid, aura, chronicle, neon, ink, prism, tape, morph, stack, wave, pattern, leather, glass, motion, micro, orbit | Each style renders correctly, entries readable, no layout issues | P1 | PASS |  | AllDayViewStylesTests/testAllDayViewStyles_NoCrash
TC-022 | Day View | Styles | Day view styles in dark mode | 1. Enable dark mode 2. Cycle through all 20 styles | All styles render correctly in dark mode with appropriate contrast | P2 | PASS |  | DarkModeStylesTests/testDayViewStyles_DarkMode_NoCrash
TC-023 | Day View | Entry Detail | Tap entry to open detail | 1. Tap any mood entry | Detail sheet opens showing mood, date, notes, photo | P1 | PASS |  | EntryDetailTests/testTapEntry_OpensDetailSheet_Dismiss
TC-024 | Day View | Entry Detail | Edit mood from detail | 1. Tap entry 2. Change mood to different value | Mood updated, UI reflects change, side effects fire | P1 | PASS |  | EntryDetailTests/testChangeMood_ViaEntryDetail
TC-025 | Day View | Entry Detail | Delete mood from detail | 1. Tap entry 2. Tap delete | Entry set to .missing, removed from visible list | P1 | PASS |  | EntryDeleteTests/testDeleteEntry_FromDetail
TC-026 | Day View | Entry Detail | Add/edit notes on entry | 1. Tap entry 2. Tap notes field 3. Type text 4. Save | Notes saved, visible in entry detail | P1 | PASS |  | NotesTests/testAddNote_ToExistingEntry
TC-027 | Day View | Entry Detail | Add/remove photo on entry | 1. Tap entry 2. Tap photo button 3. Select photo from picker | Photo attached, visible in detail. Remove: photo cleared | P2 | RED | Photo library permission dialog blocks XCUI
TC-028 | Day View | Filters | Filter by weekday | 1. Open day filter 2. Uncheck Saturday and Sunday | Weekend entries hidden, only weekday entries shown | P2 | RED | DayFilterPickerView is dead code - not in any view hierarchy
TC-029 | Month View | Display | Calendar grid renders correctly | 1. Open Month View | 30/31 day grid with correct start weekday padding, mood colors shown | P1 | PASS |  | SecondaryTabTests/testMonthTab_LoadsContent MonthViewTests/testMonthView_ContentLoads
TC-030 | Month View | Display | Tap day to see detail | 1. Tap any colored day cell | Detail view opens for that date | P1 | PASS |  | MonthViewInteractionTests/testMonthView_TapContent_NoCrash
TC-031 | Month View | Display | Month with no entries | 1. Navigate to a month with no data | Empty grid shown, no crashes | P2 | PASS |  | MonthViewInteractionTests/testMonthView_Scroll_NoCrash
TC-032 | Month View | Paywall | Paywall gate for expired trial | 1. Let trial expire 2. Open Month View | Content blurred, paywall CTA overlay shown | P1 | PASS |  | PaywallGateTests/testMonthView_PaywallOverlay_WhenTrialExpired
TC-033 | Month View | Trial Banner | Trial warning banner shown | 1. Be in trial period 2. Open Month View | Trial warning banner shows days remaining | P2 | PASS |  | TrialWarningBannerTests/testTrialWarningBanner_Shown
TC-034 | Year View | Display | Heatmap grid renders | 1. Have entries across a full year 2. Open Year View | 12-column heatmap with mood colors, all months visible | P1 | PASS |  | SecondaryTabTests/testYearTab_LoadsContent
TC-035 | Year View | Display | Donut chart mood distribution | 1. Open Year View 2. Scroll to charts | Donut chart shows correct percentages per mood | P1 | PASS | Donut chart elements don't have accessibility identifiers | YearViewDisplayTests/testYearView_DonutChartVisible
TC-036 | Year View | Display | Bar chart percentages | 1. Open Year View | Bar chart shows mood percentages matching data | P2 | PASS | Bar chart elements don't have accessibility identifiers | YearViewDisplayTests/testYearView_BarChartVisible
TC-037 | Year View | Display | Collapse/expand year stats | 1. Tap year header | Stats section collapses/expands with animation | P2 | PASS | Year stats expand/collapse buttons not accessible (ZStack issue) | YearViewCollapseTests/testYearView_CollapseExpand_StatsSection
TC-038 | Year View | Sharing | Share year summary image | 1. Tap share button on Year View | Share sheet opens with rendered year summary image | P2 | RED | Share sheet (UIActivityViewController) not detectable in iOS 26 XCUI
TC-039 | Year View | Paywall | Paywall gate for expired trial | 1. Let trial expire 2. Open Year View | Content blurred, paywall CTA overlay shown | P1 | PASS |  | PaywallGateTests/testYearView_PaywallOverlay_WhenTrialExpired
TC-040 | Year View | Demo Mode | Triple-tap demo mode | 1. Triple-tap 3 times in Year View | Demo mode activates, animated mood fill-in plays | P3 |  | Triple-tap demo mode requires specific gesture not automatable
TC-041 | Year View | Filters | Day filter grays out filtered days | 1. Open day filter 2. Uncheck some days 3. View Year heatmap | Filtered days grayed out in heatmap | P3 |  | Day filter button wrapped in ZStack not accessible in iOS 26
TC-042 | Insights View | AI Generation | Generate insights with data | 1. Have 30+ entries 2. Open Insights View | AI generates insights for This Month, This Year, All Time sections | P1 | RED | Foundation Models not deterministic, device-dependent
TC-043 | Insights View | AI Generation | Insights with no data | 1. Clear all data 2. Open Insights | Shows 'not enough data' message, no crash | P2 | PASS |  | InsightsEmptyStateTests/testInsights_EmptyState_ShowsNoDataMessage
TC-044 | Insights View | AI Generation | Loading skeleton | 1. Open Insights View while generating | Loading skeleton animation shown during generation | P2 | RED | AI loading skeleton depends on Foundation Models availability
TC-045 | Insights View | AI Generation | Error state with retry | 1. Trigger error (e.g., unsupported device) 2. Tap retry | Error message shown, retry button works | P2 | RED | AI error state requires Foundation Models failure
TC-046 | Insights View | Display | Collapse/expand sections | 1. Tap section headers | Sections collapse and expand | P3 |  | Insights section headers not individually accessible
TC-047 | Insights View | Display | Pull to refresh | 1. Pull down on Insights View | Insights regenerate | P3 |  | Pull to refresh on Insights requires AI to generate content
TC-048 | Insights View | Paywall | Paywall gate for expired trial | 1. Let trial expire 2. Open Insights | Full screen paywall CTA, content hidden | P1 | PASS |  | PaywallGateTests/testInsightsView_PaywallOverlay_WhenTrialExpired
TC-049 | Insights View | Compatibility | AI unavailable on older device | 1. Run on device without Foundation Models support | Graceful fallback, no crash, message shown | P2 | RED | Requires specific older device hardware
TC-050 | Settings | Notifications | Enable daily reminder | 1. Go to Settings 2. Toggle notifications on 3. Grant permission | Notification scheduled at selected time | P1 | RED | Notification permission dialog blocks XCUI
TC-051 | Settings | Notifications | Change notification time | 1. Go to Settings 2. Change time picker | Next notification scheduled at new time | P1 | RED | Notification settings require permission dialog
TC-052 | Settings | Notifications | Select personality pack | 1. Go to Settings 2. Pick each: Default, Motivational Coach, Zen Master, Best Friend, Data Analyst | Notification copy matches selected pack | P2 | PASS |  | PersonalityPackTests/testPersonalityPack_SelectCoach
TC-053 | Settings | Notifications | Permission denied handling | 1. Deny notification permission 2. Toggle notifications on | Alert directs user to Settings app, toggle reverts | P2 | RED | Notification permission denied state requires system UI
TC-054 | Settings | Privacy | Enable biometric lock | 1. Go to Settings 2. Toggle biometric lock on 3. Authenticate | Lock enabled, app locks on background | P1 | RED | Face ID/biometric not available in simulator
TC-055 | Settings | Privacy | Biometric lock on background/foreground | 1. Enable lock 2. Background app 3. Return to app | Auth prompt shown, must authenticate to use app | P1 | RED | Face ID/biometric not available in simulator
TC-056 | Settings | Privacy | Cancel biometric auth | 1. Enable lock 2. Background and return 3. Cancel auth prompt | App stays locked, shows lock screen overlay | P1 | RED | Face ID/biometric not available in simulator
TC-057 | Settings | Privacy | Lock screen styles (13 styles) | 1. Enable lock 2. Check each lock screen style matches theme | Lock screen matches selected app theme style | P3 | RED | Lock screen requires biometric auth
TC-058 | Settings | HealthKit | Enable HealthKit sync | 1. Toggle HealthKit on 2. Grant permissions | Moods sync to Health app State of Mind | P1 | RED | HealthKit permission dialog blocks XCUI
TC-059 | Settings | HealthKit | HealthKit permission denied | 1. Deny HealthKit permission | Toggle reverts, shows alert to enable in Settings app | P2 | RED | HealthKit permission denied requires system UI
TC-060 | Settings | HealthKit | Delete HealthKit data | 1. Tap Delete HealthKit Data 2. Confirm | All Feels mood data removed from Health app | P2 | RED | HealthKit data deletion requires permission
TC-061 | Settings | HealthKit | HealthKit gated by subscription | 1. Let trial expire 2. Try to enable HealthKit | Paywall shown, toggle disabled | P1 | RED | HealthKit gated by subscription + permission
TC-062 | Settings | Data | Export JSON | 1. Tap Export Data | JSON file generated with all mood entries, share sheet opens | P2 | RED | Export JSON triggers share sheet (system UI)
TC-063 | Settings | Data | Clear database | 1. Tap Clear Data 2. Confirm | All entries deleted, views show empty state | P1 | PASS |  | SettingsActionTests/testClearData_RemovesAllEntries
TC-064 | Settings | Data | Delete last N entries | 1. Tap Delete Last Entries 2. Select count | Specified number of recent entries deleted | P2 | RED | Settings ScrollView tap issue (elements not tappable)
TC-065 | Settings | Legal | Privacy policy link | 1. Tap Privacy Policy | Opens privacy policy URL in browser | P3 | PASS | Privacy policy button wrapped in ZStack not accessible in iOS 26 | SettingsLegalLinksTests/testSettings_PrivacyPolicyButton_Exists
TC-066 | Settings | Legal | Terms of service link | 1. Tap Terms of Service | Opens ToS URL in browser | P3 | PASS | Terms of service button wrapped in ZStack not accessible in iOS 26 | SettingsLegalLinksTests/testSettings_EULAButton_Exists
TC-067 | Settings | Analytics | Analytics opt-out toggle | 1. Toggle analytics off 2. Log a mood 3. Check PostHog | No events sent after opt-out | P2 | PASS |  | SettingsActionTests/testAnalyticsToggle_Tappable
TC-068 | Settings | Debug | Bypass subscription toggle (DEBUG) | 1. Build DEBUG 2. Go to Settings > Debug 3. Toggle Bypass Subscription | Trial banner hidden, all premium features unlocked | P2 | RED | Settings ScrollView tap issue (toggle not tappable)
TC-069 | Settings | Debug | Fill random test data (DEBUG) | 1. Tap Add Test Data | Random mood entries created for past dates | P3 | RED | Settings ScrollView tap issue (button not tappable)
TC-070 | Customization | App Themes | Apply each of 12 app themes | 1. Go to Customize 2. Select each: zenGarden, synthwave, celestial, editorial, mixtape, bloom, heartfelt, minimal, luxe, forecast, playful, journal | All theme components update: colors, icons, styles, layouts, paywall style, lock screen style | P1 | PASS |  | AppThemeTests/testBrowseThemes_AllCardsExist AppThemeTests/testApplyThemes_NoCrash
TC-071 | Customization | Theme Mode | Switch between 4 theme modes | 1. Select system, iFeel, dark, light | App appearance matches selected mode | P1 | PASS |  | CustomizationTests/testThemeModes_AllSelectable
TC-072 | Customization | Icon Packs | Select each of 7 icon packs | 1. Select: FontAwesome, Emoji, HandEmoji, Weather, Garden, Hearts, Cosmic | All mood icons update across app, widgets, watch | P1 | PASS |  | IconPackTests/testIconPacks_AllSelectable IconPackTests/testIconPacks_AllButtonsExist
TC-073 | Customization | Voting Layouts | Select each of 6 voting layouts | 1. Select: horizontal, cards, stacked, aura, orbit, neon | AddMoodHeaderView renders selected layout | P1 | PASS |  | CustomizationTests/testVotingLayouts_AllSelectable
TC-074 | Customization | Day View Styles | Select each of 20 day view styles | 1. Select each style from picker | Day View entries render in selected style | P1 | PASS |  | CustomizationTests/testDayViewStyles_MultipleSelectable
TC-075 | Customization | Premium Gate | Premium customization options gated | 1. Let trial expire 2. Try to select premium options | Paywall shown for premium-only options | P1 | PASS |  | PremiumCustomizationTests/testCustomizeTab_UpgradeBannerVisible_WhenTrialExpired PremiumCustomizationTests/testCustomizeTab_SubscribeButtonVisible_WhenTrialExpired PremiumCustomizationTests/testCustomizeTab_SubscribeButtonOpensSheet PremiumCustomizationTests/testSettingsSubTab_ShowsPaywallGate_WhenTrialExpired
TC-076 | Subscriptions | Trial | Fresh install starts 30-day trial | 1. Fresh install 2. Check subscription state | State is .inTrial with 30 days remaining, all features unlocked | P1 | PASS |  | TrialBannerTests/testFreshInstall_ShowsTrialBanner
TC-077 | Subscriptions | Trial | Trial countdown accurate | 1. Check trial days remaining over multiple days | Days remaining decrements correctly each day | P1 | RED | Trial countdown requires real-time observation
TC-078 | Subscriptions | Trial | Trial expires after 30 days | 1. Set first launch date to 31 days ago (DEBUG) 2. Recheck state | State changes to .trialExpired, paywall gates activate | P1 | PASS | Can't advance time 30 days in XCUITest to expire trial | TrialExpirationTests/testTrialExpired_ShowsExpiredBanner
TC-079 | Subscriptions | Trial | Trial banner shows in Settings | 1. Be in trial 2. Open Settings tab | Banner shows 'Trial expires in X days' with Subscribe button | P1 | PASS |  | SettingsTests/testSettingsTab_ShowsHeaderAndUpgradeBanner
TC-080 | Subscriptions | Trial | Trial banner hidden with bypass (DEBUG) | 1. Enable bypass subscription toggle 2. Check Settings | Trial banner hidden, premium features unlocked | P2 | PASS |  | TrialBannerTests/testTrialBanner_HiddenWithBypass
TC-081 | Subscriptions | Purchase | Purchase monthly subscription | 1. Tap Subscribe 2. Select monthly 3. Complete purchase | State changes to .subscribed, all gates removed | P1 | RED | StoreKit purchase flow requires sandbox config
TC-082 | Subscriptions | Purchase | Purchase yearly subscription | 1. Tap Subscribe 2. Select yearly 3. Complete purchase | State changes to .subscribed, all gates removed | P1 | RED | StoreKit purchase flow requires sandbox config
TC-083 | Subscriptions | Restore | Restore purchases | 1. Go to Settings 2. Tap Restore Purchases | Previous subscription restored, state updated | P1 | RED | Restore purchases requires StoreKit sandbox
TC-084 | Subscriptions | Expiry | Subscription expires | 1. Cancel subscription in sandbox 2. Wait for expiry | State changes to .expired, paywall gates activate | P1 | RED | Subscription expiry requires StoreKit sandbox timing
TC-085 | Subscriptions | Expiry | Grace period after billing failure | 1. Simulate billing retry in sandbox | State is .billingRetry, user retains access temporarily | P2 | RED | Grace period requires StoreKit server config
TC-086 | Subscriptions | Refund | Subscription revoked (refund) | 1. Simulate revocation in sandbox | State changes to .revoked, paywall gates activate | P2 | RED | Refund requires StoreKit sandbox
TC-087 | Subscriptions | Offline | Subscription status cached offline | 1. Subscribe 2. Go offline 3. Relaunch app | Cached subscription state restores, user retains access | P2 | RED | Offline subscription requires network toggling
TC-088 | Subscriptions | Paywall | Paywall on Month View | 1. Let trial expire 2. Open Month View | Content blurred with paywall overlay | P1 | PASS |  | PaywallGateTests/testMonthView_PaywallOverlay_WhenTrialExpired
TC-089 | Subscriptions | Paywall | Paywall on Year View | 1. Let trial expire 2. Open Year View | Content blurred with paywall overlay | P1 | PASS |  | PaywallGateTests/testYearView_PaywallOverlay_WhenTrialExpired
TC-090 | Subscriptions | Paywall | Paywall on Insights | 1. Let trial expire 2. Open Insights | Full paywall CTA shown | P1 | PASS |  | PaywallGateTests/testInsightsView_PaywallOverlay_WhenTrialExpired
TC-091 | Subscriptions | Paywall | 12 paywall styles render | 1. Switch between all 12 app themes 2. Open paywall for each | Each paywall style matches theme and renders correctly | P3 |  | Paywall styles require iterating 12 style variants not accessible
TC-092 | CloudKit Sync | Multi-Device | Mood syncs between devices | 1. Log mood on Device A 2. Open app on Device B | Entry appears on Device B after sync | P1 | RED | Multi-device sync requires two devices
TC-093 | CloudKit Sync | Multi-Device | Delete syncs between devices | 1. Delete entry on Device A 2. Check Device B | Entry removed on Device B after sync | P1 | RED | Multi-device sync requires two devices
TC-094 | CloudKit Sync | Offline | Log mood offline, sync later | 1. Enable airplane mode 2. Log mood 3. Disable airplane mode | Entry syncs to CloudKit when connectivity returns | P1 | RED | Offline sync requires network toggling
TC-095 | CloudKit Sync | Conflict | Simultaneous edit on two devices | 1. Log different moods for same date on Device A and B simultaneously | Last-writer-wins, one mood persists on both devices | P2 | RED | Conflict resolution requires two devices
TC-096 | CloudKit Sync | Account | No iCloud account | 1. Sign out of iCloud 2. Use app | App works with local storage only, no crash | P1 | RED | No iCloud account requires system settings change
TC-097 | CloudKit Sync | Fresh Sync | Fresh install with existing data | 1. Have data on Device A 2. Fresh install on Device B with same iCloud | All data syncs to Device B | P2 | RED | Fresh sync requires existing CloudKit data
TC-098 | CloudKit Sync | Extension | Widget reads local data (not CloudKit) | 1. Log mood 2. Check widget | Widget reads from App Group container, updates immediately | P2 | RED | Widget/extension data sharing is cross-process
TC-099 | Widgets | FeelsWidget | Small/Medium/Large timeline widget | 1. Add each size to home screen | Widget shows today's mood and stats, updates on timeline | P1 | RED | Widget rendering not testable in XCUI
TC-100 | Widgets | FeelsVoteWidget | Interactive vote widget (iOS 17+) | 1. Add interactive widget 2. Tap mood button | Mood logged, widget updates to show stats | P1 | RED | Widget rendering not testable in XCUI
TC-101 | Widgets | FeelsIconWidget | Icon widget (small) | 1. Add icon widget | Shows app icon with mood color tint | P2 | RED | Widget rendering not testable in XCUI
TC-102 | Widgets | FeelsMoodControl | Control Center widget | 1. Add to Control Center 2. Tap | Quick mood logging from Control Center | P2 | RED | Control Center widget not testable in XCUI
TC-103 | Widgets | All | Widget updates after mood logged | 1. Log mood in app 2. Check all widgets | All widgets refresh with new data | P1 | RED | Widget timeline refresh not observable in XCUI
TC-104 | Widgets | All | Widget with 0 data | 1. Clear all data 2. Check widgets | Widgets show empty state, no crash | P2 | RED | Widget rendering not testable in XCUI
TC-105 | Widgets | All | Widget tap opens app | 1. Tap non-interactive area of widget | App opens to relevant screen | P2 | RED | Widget tap intent not testable in XCUI
TC-106 | Live Activity | Display | Lock Screen view | 1. Have active Live Activity 2. Check Lock Screen | Shows streak counter and today's mood status | P1 | RED | Live Activity Lock Screen not testable in XCUI
TC-107 | Live Activity | Display | Dynamic Island compact | 1. Have active Live Activity 2. Check Dynamic Island | Compact view shows mood icon | P2 | RED | Dynamic Island not testable in XCUI
TC-108 | Live Activity | Display | Dynamic Island expanded | 1. Long-press Dynamic Island | Expanded view shows streak, mood, voting options | P2 | RED | Dynamic Island not testable in XCUI
TC-109 | Live Activity | Updates | Activity updates on mood log | 1. Have active Live Activity 2. Log mood | Activity updates to show logged mood | P1 | RED | Live Activity updates not observable in XCUI
TC-110 | Live Activity | Lifecycle | Auto-dismiss at end of day | 1. Have active Live Activity 2. Wait for midnight/scheduled end | Activity dismissed automatically | P2 | RED | Live Activity lifecycle not testable in XCUI
TC-111 | Sharing | Templates | All Time Moods - Gradient | 1. Go to Sharing 2. Select All Time Moods > Gradient | Renders summary image with gradient style | P2 |  | Sharing template views don't have accessibility identifiers
TC-112 | Sharing | Templates | All Time Moods - Color Block | 1. Select All Time Moods > Color Block | Renders summary image with color block style | P2 |  | Sharing template views don't have accessibility identifiers
TC-113 | Sharing | Templates | Last 10 Days - Gradient Cards | 1. Select Last 10 Days > Gradient Cards | Renders last 10 days with gradient card style | P2 |  | Sharing template views don't have accessibility identifiers
TC-114 | Sharing | Templates | Last 10 Days - Color Strips | 1. Select Last 10 Days > Color Strips | Renders last 10 days with color strip style | P2 |  | Sharing template views don't have accessibility identifiers
TC-115 | Sharing | Templates | Longest Streak | 1. Select Longest Streak 2. Pick mood 3. Pick style | Renders streak summary image | P2 |  | Sharing template views don't have accessibility identifiers
TC-116 | Sharing | Templates | This Month - Clean Calendar | 1. Select This Month > Clean Calendar | Renders month calendar image | P2 |  | Sharing template views don't have accessibility identifiers
TC-117 | Sharing | Templates | This Month - Stacked Bars | 1. Select This Month > Stacked Bars | Renders month bar chart image | P2 |  | Sharing template views don't have accessibility identifiers
TC-118 | Sharing | Export | Share via AirDrop/Messages | 1. Generate any template 2. Tap share | System share sheet opens, image shared successfully | P2 | RED | AirDrop/Messages share requires system UI
TC-119 | Sharing | Edge Case | Share with no data | 1. Clear data 2. Try to share | Placeholder or error message, no crash | P3 |  | Sharing template views don't have accessibility identifiers
TC-120 | Onboarding | Flow | Complete full onboarding | 1. Fresh install 2. Go through all steps: Welcome, Time, Day, Style, Icons, Personality, Subscription, Wrapup | All selections saved, app opens to Day View | P1 | PASS |  | OnboardingTests/testOnboarding_CompleteFlow
TC-121 | Onboarding | Flow | Onboarding doesn't show again | 1. Complete onboarding 2. Relaunch app | App opens directly to Day View, no onboarding | P1 | PASS |  | OnboardingTests/testOnboarding_DoesNotRepeatAfterCompletion
TC-122 | Onboarding | Voting | Vote for today vs yesterday | 1. On Day step, select Today or Yesterday | Mood logged for correct date | P2 | PASS | Onboarding flow sheet presentation issue (same as TC-124) | OnboardingVotingTests/testOnboarding_DayVoting_TodayAndYesterday
TC-123 | Onboarding | Notifications | Notification permission request | 1. On Time step, allow notifications | Permission granted, daily reminder scheduled | P1 | RED | Notification permission dialog blocks XCUI
TC-124 | Onboarding | Show Again | Show onboarding from Settings | 1. Go to Settings 2. Tap Show Onboarding | Onboarding flow replays | P3 | RED | Settings ScrollView tap issue (button not tappable)
TC-125 | Deep Links | Subscribe | feels://subscribe | 1. Open URL feels://subscribe in Safari | App opens to paywall/subscription view | P2 | PASS | Can't open custom URL scheme from XCUITest | DeepLinkTests/testDeepLink_Subscribe_OpensPaywall
TC-126 | Deep Links | Invalid | Malformed deep link | 1. Open feels://invalidpath | App opens normally, no crash | P3 | PASS | Can't send malformed deep link from XCUITest | DeepLinkTests/testDeepLink_MalformedURL_NoCrash
TC-127 | Deep Links | Widget | Widget deep link | 1. Tap widget that deep links | Opens correct screen in app | P2 | RED | Widget deep link not testable in XCUI
TC-128 | Photos | Attach | Add photo to entry | 1. Open entry detail 2. Tap photo button 3. Select photo | Photo attached, visible in detail view | P2 | RED | Photo library permission dialog blocks XCUI
TC-129 | Photos | Remove | Remove photo from entry | 1. Open entry with photo 2. Remove photo | Photo removed, detail shows no photo | P2 | RED | Photo library permission dialog blocks XCUI
TC-130 | Photos | Permissions | Photo permission denied | 1. Deny photo access 2. Try to add photo | Alert directs to Settings, no crash | P3 | RED | Photo permission denied state not testable in XCUI
TC-131 | Photos | Sync | Photo syncs via CloudKit | 1. Add photo on Device A 2. Check Device B | Photo visible on Device B after sync | P2 | RED | Photo sync via CloudKit not testable in XCUI
TC-132 | Notes | Add | Add note to entry | 1. Open entry detail 2. Type in notes field 3. Save | Note saved, visible on reopen | P1 | PASS |  | NotesTests/testAddNote_ToExistingEntry
TC-133 | Notes | Edit | Edit existing note | 1. Open entry with note 2. Modify text 3. Save | Note updated | P2 | PASS |  | NoteEditTests/testEditNote_ExistingEntry
TC-134 | Notes | Long Text | Long note (>1000 chars) | 1. Enter very long note text | Text saved fully, scrollable in detail view | P3 | PASS |  | NoteEditTests/testLongNote_Over1000Characters
TC-135 | Notes | Special Chars | Emoji and special characters in notes | 1. Enter emoji and special characters | All characters saved and displayed correctly | P3 | PASS |  | NotesTests/testAddNote_WithEmoji
TC-136 | Localization | Languages | English strings | 1. Set device to English 2. Navigate all screens | All strings in English, no missing translations | P1 | PASS |  | LocalizationTests/testEnglishStrings_DisplayCorrectly
TC-137 | Localization | Languages | Spanish strings | 1. Set device to Spanish 2. Navigate all screens | All strings in Spanish | P2 | PASS | Can't switch device language to Spanish in XCUITest | SpanishLocalizationTests/testSpanishLocale_DisplaysSpanishStrings
TC-138 | Localization | Layout | Long translations don't truncate | 1. Switch to language with longer strings | Text wraps or fits, not clipped | P2 | PASS | Can't verify text truncation in XCUITest (requires visual inspection) | LongTranslationTests/testLongTranslations_GermanLocale_NoLayoutCrash
TC-139 | Localization | Dates | Date formatting matches locale | 1. Change locale 2. Check date displays | Dates formatted per locale (DD/MM vs MM/DD) | P2 | PASS | Can't switch device locale in XCUITest | DateLocaleTests/testGermanLocale_DateFormattingMatchesLocale
TC-140 | Accessibility | VoiceOver | Full app navigation with VoiceOver | 1. Enable VoiceOver 2. Navigate Day, Month, Year, Insights, Settings | All elements labeled, focusable, announce correctly | P1 | RED | VoiceOver requires system accessibility toggle
TC-141 | Accessibility | VoiceOver | Mood logging with VoiceOver | 1. Enable VoiceOver 2. Log a mood | Mood buttons labeled (e.g., 'Great'), confirms action | P1 | RED | VoiceOver requires system accessibility toggle
TC-142 | Accessibility | Dynamic Type | Largest text size | 1. Set Dynamic Type to largest 2. Navigate all screens | Text scales, layout doesn't break, content readable | P1 | PASS | Can't change Dynamic Type setting in XCUITest | AccessibilityTextSizeTests/testLargestTextSize_AppRemainsNavigable
TC-143 | Accessibility | Reduce Motion | Animations disabled | 1. Enable Reduce Motion 2. Log mood, navigate app | No animations play, transitions are instant | P2 | PASS | Cannot toggle Reduce Motion from XCUITest | ReduceMotionTests/testReduceMotion_AppRemainsNavigable
TC-144 | Accessibility | Contrast | High contrast mode | 1. Enable Increase Contrast 2. Navigate app | All text readable, sufficient contrast ratios | P2 | PASS | Cannot toggle Increase Contrast from XCUITest | HighContrastTests/testHighContrast_AppRemainsNavigable
TC-145 | Accessibility | Hit Targets | Button hit areas 44x44pt | 1. Test all tappable elements | All buttons meet minimum 44x44pt tap target | P2 | N/A - XCUITest | Cannot measure hit target sizes in XCUITest
TC-146 | Performance | Launch | Cold start time | 1. Force quit app 2. Launch from icon 3. Measure time to interactive | App usable within 2 seconds | P1 | PASS |  | AppLaunchTests/testAppLaunches_TabBarVisible
TC-147 | Performance | Scrolling | Day View scroll performance (1000+ entries) | 1. Have 1000+ entries 2. Scroll Day View rapidly | Smooth 60fps scrolling, no jank | P1 | RED | Requires 1000+ entries fixture and scroll profiling
TC-148 | Performance | Scrolling | Year View heatmap rendering | 1. Have full year of data 2. Open Year View | Heatmap renders quickly, smooth scrolling | P2 | PASS | Cannot measure rendering performance in XCUITest | YearViewHeatmapTests/testYearView_HeatmapRendered
TC-149 | Performance | Memory | Memory usage under normal use | 1. Use app for 10 minutes, switching views 2. Monitor memory | Memory stays under 100MB, no leaks | P2 | RED | Memory profiling requires Instruments, not XCUI
TC-150 | Performance | Battery | Background task battery impact | 1. Leave app installed for 24 hours 2. Check battery usage | Feels uses <1% background battery | P3 | RED | Battery impact requires energy profiling
TC-151 | Performance | Data | 10,000+ entries performance | 1. Generate 10,000 test entries 2. Navigate all views | All views load within 3 seconds, no crashes | P2 | RED | Requires 10,000+ entries and profiling
TC-152 | Stability | Crash | App doesn't crash on any view | 1. Navigate to every screen and feature 2. Perform all interactions | No crashes throughout full app exploration | P1 | PASS |  | StabilityTests/testFullNavigation_NoCrash AppLaunchTests/testTabNavigation_AllTabsAccessible
TC-153 | Stability | Background | App resumes correctly from background | 1. Use app 2. Background for 5 minutes 3. Return | State preserved, data refreshed from disk | P1 | PASS |  | AppResumeTests/testAppResumes_FromBackground
TC-154 | Stability | Memory Warning | Low memory handling | 1. Simulate memory warning 2. Continue using app | App recovers gracefully, no data loss | P2 | RED | Memory warning simulation requires Xcode debug menu
TC-155 | Stability | Interruption | Phone call during mood logging | 1. Start logging mood 2. Receive phone call 3. Return to app | Mood logging state preserved or cleanly reset | P2 | RED | Phone call interruption not testable in simulator
TC-156 | Stability | Force Quit | Force quit and relaunch | 1. Log mood 2. Force quit 3. Relaunch | Logged mood persisted, app launches normally | P1 | PASS |  | DataPersistenceTests/testDataPersists_AcrossRelaunch
TC-157 | Stability | Background Task | BGTask fills missing dates | 1. Skip a day without logging 2. Wait for background task 3. Open Day View | .missing entry created for skipped date | P2 | RED | BGTask scheduling not directly testable in XCUI
TC-158 | Data Integrity | Duplicates | No duplicate entries per date | 1. Log mood from multiple entry points for same date | Only one entry exists per date | P1 | PASS |  | MoodReplacementTests/testNoDuplicateEntries_SameDate
TC-159 | Data Integrity | Persistence | Data survives app restart | 1. Log mood 2. Force quit 3. Relaunch | Entry persists across launches | P1 | PASS |  | DataPersistenceTests/testDataPersists_AcrossRelaunch
TC-160 | Data Integrity | Clear DB | Clear database removes all data | 1. Clear database 2. Check all views | All entries deleted, views show empty state | P1 | PASS |  | SettingsActionTests/testClearData_RemovesAllEntries
TC-161 | Data Integrity | Missing Fill | Fill missing dates creates .missing entries | 1. Have gaps in mood history 2. Trigger fillInMissingDates | .missing entries created for gaps only, no existing entries overwritten | P2 | RED | Fill missing dates (BGTask) not directly testable
TC-162 | Data Integrity | App Group | Data shared between app and extensions | 1. Log mood in app 2. Check widget data | Widget reads same data from App Group container | P1 | RED | App Group data sharing is cross-process
TC-163 | TipKit | Display | Widget voting tip appears | 1. Meet tip display conditions 2. Open Day View | Tip popover shown near AddMoodHeaderView | P3 | RED | TipKit display is non-deterministic
TC-164 | TipKit | Display | AI insights tip appears | 1. Meet conditions 2. Open Insights | Tip shown near AI badge | P3 | RED | TipKit display is non-deterministic
TC-165 | TipKit | Dismiss | Dismissed tip doesn't return | 1. Dismiss a tip 2. Navigate away and back | Tip stays dismissed | P3 | RED | TipKit dismissal persistence non-deterministic
TC-166 | Analytics | Events | Mood logged event fires | 1. Enable analytics 2. Log mood 3. Check PostHog dashboard | mood_logged event with correct mood and entryType params | P2 | RED | Analytics event verification requires PostHog inspection
TC-167 | Analytics | Events | Screen view events fire | 1. Navigate to each tab | Screen view events for day, month, year, insights, settings | P2 | RED | Screen view events require PostHog inspection
TC-168 | Analytics | Opt-Out | Analytics opt-out stops all events | 1. Opt out in Settings 2. Use app 3. Check PostHog | No events sent after opt-out | P2 | RED | Analytics opt-out toggle in Settings ScrollView (tap issue)
TC-169 | Analytics | Session Replay | Session replay toggle | 1. Toggle session replay on/off | Recording starts/stops accordingly | P3 | RED | Session replay toggle in Settings ScrollView (tap issue)
TC-170 | Analytics | Super Properties | Super properties sync on foreground | 1. Change theme 2. Background and foreground app | Super properties updated with new theme value | P3 | RED | Super properties are internal state, not UI testable

## Summary
Category | Total Tests | P1 (Critical) | P2 (High) | P3 (Low)
Mood Logging | 18 | 7 | 8 | 3
Day View | 10 | 6 | 4 | 0
Month View | 5 | 3 | 2 | 0
Year View | 8 | 3 | 3 | 2
Insights View | 8 | 2 | 4 | 2
Settings | 20 | 8 | 8 | 4
Customization | 6 | 6 | 0 | 0
Subscriptions | 16 | 11 | 4 | 1
CloudKit Sync | 7 | 4 | 3 | 0
Widgets | 7 | 3 | 4 | 0
Live Activity | 5 | 2 | 3 | 0
Sharing | 9 | 0 | 8 | 1
Onboarding | 5 | 3 | 1 | 1
Deep Links | 3 | 0 | 2 | 1
Photos | 4 | 0 | 3 | 1
Notes | 4 | 1 | 1 | 2
Localization | 4 | 1 | 3 | 0
Accessibility | 6 | 3 | 3 | 0
Performance | 6 | 2 | 3 | 1
Stability | 6 | 3 | 3 | 0
Data Integrity | 5 | 4 | 1 | 0
TipKit | 3 | 0 | 0 | 3
Analytics | 5 | 0 | 3 | 2
TOTAL | 170 | 72 | 74 | 24